## Sheet1
Serial No | To Do List | Features | Date | Priority
1 | Research Technologies | Finalizing all the technologies to be used in the project | 9/6/2020-9/9/2020 | High
2 | Requirements gathering | Gathering all the requirements related to project | 9/13/2020-9/18/2020 | High
3 | Decide on modules to be used in project | deciding on using modules like admin/faculty/ | 9/13/2020-9/18/2020 | High
4 | Design user interface of applicaion | we have designed the user interface of application | 9/22/2020-9/26/2020 | High
5 | Create home page of application | We have created home page of the application for admin and faculty | 9/27/2020-10/03/2020 | High
6 | work on database | we have designed the database to store student and faculty details | 10/04/2020-10/10/2020 | High
7 | Create admin login and options page | we have created admin login page and options page for admin which should be displayed after login | 10/04/2020-10/23/2020 | High
8 | Create student registration page | We have created student registration page | 10/04/2020-10/25/2020 | High
9 | Draft the technical paper of project | We have draafted the technical paper which provides information on design and technologies used in project | 10/10/2020-10/26/2020 | High
10 | Create faculty login and registration page | we have created faculty login and registration page | 11/4/2020-11/16/2020 | High
11 | Add functionality to store details | We have added functionality to capture student image and students details into the database | 10/29/2020-11/11/2020 | High
12 | view students page | We have added functionality to view the students registered in the database | 11/12/2020-11/20/2020 | High